## ACEP-ALE timeline
EASEMENT PROGRAM |  |  | FY2022
General Easement (ACEP-ALE) | Responsible Person(s) | December | January | February | March | April | May | June | July | August | September
ACEP-ALE Signup Announcement (open minimum 30 days) | NRCS | December: 2021-12-17
ACEP-ALE Q&A Session with Interested Applicants | NRCS | FY2022 January: 2022-01-13
Application packet deadline | Entity | FY2022 February: 2022-02-25
FSA Eligibility (AGI, AD1026, FTE, 901/902)-- These categories must be "Yes" in Protracts. SAM/DUNs active requirement for Land Trusts | Entity and all Landowner(s) on deed | FY2022 March: 2022-03-04
Screening completed | NRCS | FY2022 March: 2022-03-11
CART Assessment/Ranking/Cost est. completed | NRCS | FY2022 April: 2022-04-01
EPM selects program and/or parcel applications for Pre-Approval | NRCS | FY2022 April: 2022-04-15
Field site visits, offered land eligiblity determination, planning | NRCS | FY2022 May: 2022-05-20
Pre-obligation checklist completed and documents uploaded to PAMs | NRCS | FY2022 July: 2022-07-01
Program and/or Parcel Agreement selection deadline date | NRCS | FY2022 August: 2022-08-05
Entity returns signed Program and/or Parcel Agreement documents deadline date | Entity | FY2022 August: 2022-08-19
NRCS deadline of initial allocation to obligate Program and/or Parcel Agreement | NRCS | FY2022 August: 2022-08-31